## Sheet1
Finding | Corrective Action | Owner | Priority | Target Date | Status | Evidence Required
Incomplete Data Inventory (Missing Systems) | Conduct a comprehensive discovery exercise across all departments to identify and document all personal data processing systems. | GRC Manager | High | 2026-09-30 | In Progress | Updated Data Inventory Spreadsheet
Gaps in Cloud Data Flow Mapping | Perform a technical review of cloud architecture and document all cross-border and internal data flows for personal data. | Privacy Lead | High | 2026-09-15 | Open | Verified Data Flow Diagrams
Undocumented Processing Purposes | Review the Processing Register and interview business owners to document legal basis and purpose for all identified activities. | Privacy Lead | High | 2026-08-20 | In Progress | Signed Processing Register
Missing Data Retention Periods | Establish a formal Data Retention Policy and define specific retention schedules for all major datasets. | GRC Manager | High | 2026-10-30 | Open | Approved Retention Schedule
Inconsistent Evidence of Secure Deletion | Implement a standardized process for data sanitization and maintain central logs for all deletion requests and automated purges. | IT Manager | High | 2026-09-10 | Open | Deletion Logs / Certificates of Destruction
Privacy Incident Escalation Needs Testing | Conduct a tabletop exercise specifically for personal data breaches to validate the escalation and notification procedures. | Security Manager | Medium | 2026-08-15 | Scheduled | Tabletop Exercise Report
Overdue Vendor Risk Assessments | Launch a remediation project to assess all high-risk vendors and update contracts with mandatory PDPL clauses. | GRC Manager | High | 2026-11-30 | Open | Completed Vendor Assessment Reports